## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
Proyecto Final: Yelp & Google Maps - Reseñas y Recomendaciones
Insightful Data Solutions |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2024-06-10 |  |  |  |  | June | [20 empty] | July
Scrolling increment: | 1 |  |  |  |  | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Sprint # 1
Situacion Actual | On Track | (RS) | 100% | 2024-06-11 | 2
Objetivos | On Track | (RS) | 100% | 2024-06-11 | 2
Alcance y KPIs Asociados | Low Risk | (RS) | 80% | 2024-06-13 | 2
Reporsitorio Github | On Track | (RS) | 100% | 2024-06-13 | 1
Solucion Propuesta (Productos, tecnologias a Utilizar) | Low Risk | (RS), (AD), (CA) | 80% | 2024-06-13 | 3
Diagrama de Gantt | On Track | (RS) | 100% | 2024-06-16 | 1
EDA preliminar | Low Risk | (JE), (RR) | 50% | 2024-06-14 | 5
Presentacion | On Track | (RS) | 30% | 2024-06-16 | 7
Sprint # 2
Diccionario de datos | Milestone | (RS), (AD), (CA) | 0% | 2024-06-24 | 3 | bar: 2024-06-24 to 2024-06-26
Analisis de Muestra representativa de datos | On Track | (JE), (RR) | 0% | 2024-06-22 | 3
ETL y Pipelines | On Track | (AD), (CA) | 0% | 2024-06-22 | 6
Arquitectura propuesta | On Track | (AD), (CA) | 0% | 2024-06-24 | 2
Data Warehouse con carga inicial | On Track | (AD), (CA) | 0% | 2024-06-27 | 5
Carga Incremental de Datos | On Track | (AD), (CA) | 0% | 2024-06-27 | 6
Modelo Entidad Relacion | On Track | (AD), (CA) | 0% | 2024-06-28 | 2
Modelo de ML y Dashboard: Version de prueba | On Track | (AD), (CA), (RS) | 0% | 2024-07-02 | 3
Servicios Cloud y/o big data | On Track | (AD), (CA) | 0% | 2024-06-28 | 2
Sprint # 3
Diseño de Reporets/Dashboards | Milestone | (JE), (RR) | 0% | 2024-07-06 | 4 | bar: 2024-07-06 to 2024-07-09
Modelo ML | On Track | (DG) | 0% | 2024-07-06 | 6
Modelo de ML en produccion | On Track | (DG) | 0% | 2024-07-10 | 8
Documentacion: Seleccion del modelo, feature engineering, informe de analisis | On Track | (RS), (AD), (CA), (DG) | 0% | 2024-07-10 | 3
Presentaciones + Storytelling + documentacion | On Track | (RS), (AD), (CA), (DG), (JE), (RR) | 0% | 2024-07-13 | 2
Repos ordenados (readme completo) | Goal | (RS) | 0% | 2024-07-16 | 4 | 2024-07-16: 2; 2024-07-17: 2; 2024-07-18: 2; 2024-07-19: 2
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2024-06-16 |  |  |  |  | June | [13 empty] | July | [27 empty] | August
Scrolling increment: | 5 | time axis 2024-06-21 to 2024-08-15
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
TITLE 1
Task 1 | Goal | Name | 25% | 2024-06-16 | 3
Task 2 | Milestone |  |  | 2024-06-21 | 1 | bar: F
Task 3 | Low Risk |  | 50% | 2024-06-13 | 10
Task 4 | Milestone |  |  | 2024-07-06 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2024-06-22 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-22 | 13
Task 2 | On Track |  | 50% | 2024-06-24 | 9
Task 3 | Low Risk |  | 33% | 2024-06-29 | 11
Task 4 | Milestone |  |  | 2024-07-01 | 1 | bar: M
Task 5 |  |  |  | 2024-07-02 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-07-01 | 4
Task 2 | Med Risk |  |  | 2024-07-04 | 14
Task 3 | On Track |  |  | 2024-07-19 | 6
Task 4 | Goal |  |  | 2024-07-23 | 3 | T: 2; W: 2; T: 2
Task 5 | Low Risk |  |  | 2024-06-22 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-26 | 15
Task 2 |  |  |  | 2024-08-09 | 5
Task 3 | Milestone |  |  | 2024-09-20 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2024-06-16 |  |  |  |  | June | [13 empty] | July | [27 empty] | August
Scrolling increment: | 5 | time axis 2024-06-21 to 2024-08-15
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-21 to 2024-08-15
TITLE 1
Task 1 | Goal | Name | 25% | 2024-06-16 | 3
Task 2 | Milestone |  |  | 2024-06-21 | 1 | bar: 2024-06-21
Task 3 | Low Risk |  | 50% | 2024-06-13 | 10
Task 4 | Milestone |  |  | 2024-07-06 | 1 | bar: 2024-07-06
Task 5 | Med Risk |  | 10% | 2024-06-22 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-22 | 13
Task 2 | On Track |  | 50% | 2024-06-24 | 9
Task 3 | Low Risk |  | 33% | 2024-06-29 | 11
Task 4 | Milestone |  |  | 2024-07-01 | 1 | bar: 2024-07-01
Task 5 |  |  |  | 2024-07-02 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-07-01 | 4
Task 2 | Med Risk |  |  | 2024-07-04 | 14
Task 3 | On Track |  |  | 2024-07-19 | 6
Task 4 | Goal |  |  | 2024-07-23 | 3 | 2024-07-23: 2; 2024-07-24: 2; 2024-07-25: 2
Task 5 | Low Risk |  |  | 2024-06-22 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-26 | 15
Task 2 |  |  |  | 2024-08-09 | 5
Task 3 | Milestone |  |  | 2024-09-20 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one